## Test Results
SmartEPT - Gate-to-PC Manual Test Results
Fill in the four shaded columns (Result, Tested by, Date, Notes). Everything else is the script - please don't change it.
Companion document: SmartEPT-Gate-Manual-Test-Plan-2026-08-19.pdf - read section 4 before starting.
ID | Group | Test case | Severity | Setup / preconditions | Steps | Expected result | Result | Tested by | Date | Notes / what actually happened
Group A - Attendance source — the reported bug
A1 | A | Baseline: a gated company walls the agent | Critical | Org = With biometric device; Gate mode = Always ON; Employee A has no punch today. | Sign the agent in as Employee A on the test PC. | Agent shows "Punch in at the door to start". No work session begins.
A2 | A | Switching to Without biometric device releases the agent | Critical | Continue from A1, agent still showing the wall. | Organisation -> Attendance source -> Without biometric device -> Save. Do not restart the agent. | Within ~15s the wall disappears by itself and the session starts. No restart / unbind / re-login needed.
A3 | A | Biometric and Gate Exclusions menus hide themselves | Medium | Still on Without biometric device. | Hard-refresh the console (Ctrl+F5), sign in, look at the sidebar. | Biometric and Gate Exclusions are both absent. All other menus unchanged.
A4 | A | Switching back restores the gate | High | - | Organisation -> With biometric device -> Save. Hard-refresh. Watch the agent. | Both menus reappear. Within ~15s the agent shows the wall again.
A5 | A | Leftover reader records do not keep the gate on | Critical | A biometric device is configured and Active (do NOT delete it). Gate mode = Always ON. | Organisation -> Without biometric device -> Save. Watch the agent. | Agent released within ~15s despite the device record and the Always ON setting.
Group B - The Gate Exclusions screen
B1 | B | The menu is in the right place | Low | - | Look at the sidebar under Manage. Click Gate Exclusions. | Appears directly below Biometric. Screen opens, titled Gate Exclusions.
B2 | B | The status card tells the truth | Medium | Gate mode = Always ON. | Read the top card. Then set Gate mode = OFF, Save, return and re-read. | First: Gate-to-PC is ON (green). Then: Gate-to-PC is OFF (amber) with a warning that exclusions have no effect.
B3 | B | Empty state | Low | No exclusions created yet. | Look at the table. | Plain-language message that there are no exclusions - not a blank table, not an error.
B4 | B | Create an exclusion for one employee | High | Gate mode = Always ON. | + Add exclusion -> Employee -> Employee A -> Excluded -> no dates -> reason -> Save. | Row appears: Employee, name, Excluded, dashes for dates, Status Active, your reason, your name under Granted by.
B5 | B | The excluded employee is released | Critical | B4 done; Employee A has no punch today. | Watch the agent for 20 seconds. | Wall disappears within ~15s; work session starts.
B6 | B | Removing the exclusion re-gates them | Critical | B5 done. | Gate Exclusions -> Remove -> confirm. Watch the agent. | Row disappears. Within ~15s the agent shows the wall again.
Group C - Levels and precedence
C1 | C | A branch exclusion covers everyone at that site | High | No other exclusions. | + Add exclusion -> Branch -> Employee A's branch -> Excluded -> Save. Watch the agent. | Agent released within ~15s, with no personal exclusion on Employee A.
C2 | C | A team marked Required stays behind the gate | Critical | C1 in place, Employee A working. | + Add exclusion -> Team -> Employee A's team -> Required -> Save. Watch the agent. | Within ~15s the agent returns to the wall, even though the branch above is Excluded.
C3 | C | A personal exclusion beats the team requirement | High | C1 and C2 both in place. | + Add exclusion -> Employee -> Employee A -> Excluded -> Save. Watch the agent. | Released within ~15s. Employee is more specific than Team.
C4 | C | Colleagues are NOT affected | Critical | Remove the Branch and Team rows. Leave only Employee A's personal exclusion. | Sign the agent in as Employee B (no punch today). | Employee B sees the wall. The exclusion must not leak to anyone else.
C5 | C | One machine only | Medium | No other exclusions. | + Add exclusion -> Machine -> the test PC -> Excluded -> Save. Watch the agent. | Released within ~15s. Then remove it.
Group D - Dates
D1 | D | A future-dated exclusion does nothing yet | High | No other exclusions; Employee A walled. | Add: Employee A, Excluded, Valid from = tomorrow, Valid until = a week from tomorrow. | Status reads Scheduled. Agent stays on the wall.
D2 | D | An exclusion covering today applies | High | D1 row exists. | Edit the row -> Valid from = today -> Save. | Status changes to Active; agent released within ~15s.
D3 | D | An exclusion whose end date has passed does nothing | Critical | D2 row exists. | Edit -> Valid from = a week ago, Valid until = yesterday -> Save. | Status reads Expired; agent returns to the wall within ~15s.
D4 | D | An exclusion ending today still works all of today | High | D3 row exists. | Edit -> Valid from = a week ago, Valid until = today -> Save. | Status Active; agent released. The end date is inclusive.
D5 | D | Expiry happens at LOCAL midnight - overnight check | Critical | Leave the D4 exclusion (until = today) and the agent running overnight. | Check once in the evening after 18:30 and again next morning before 09:30. Record both times. | Evening: still Active and working. Next morning: Expired and walled. The change happens around local midnight - NOT at 05:30, not at 18:30.
D6 | D | An end date before the start date is refused | Medium | - | Try to save with Valid from = next Friday and Valid until = today. | Clear error message; nothing is saved.
D7 | D | Blank dates mean permanent | Medium | - | Clear both date fields on the row and Save. | Status Active, dashes for both dates, agent released, stays that way.
Group E - Reason and accountability
E1 | E | The reason and the grantor are shown | Medium | - | Create any exclusion with a reason. Read the row. | Reason shows exactly what you typed. Granted by shows your own name.
E2 | E | Whoever changes it becomes accountable for it | High | E1 row, created by you, Valid until = tomorrow. | Sign out. Sign in as a DIFFERENT admin (HR Admin). Edit the row -> Valid until = next week -> Save. | Granted by now shows the second admin. Setting still Excluded and reason unchanged - extending must not remove it.
E3 | E | Removing an exclusion clears everything with it | Low | - | Remove the row, then create a fresh exclusion on the same person with no reason and no dates. | New row shows dashes for reason and dates. No leftovers.
E4 | E | The change is in the audit log | Medium | - | Audit & Ops -> look for entries around the times you created / removed exclusions. | Changes appear as update entries against the employee / branch, attributed to the right admin.
Group F - Robustness - the defects found in review
F1 | F | A name with an apostrophe does not break the screen | High | - | Rename a test branch to O'Brien Site, give it an exclusion, press Remove. Also try a name with a double quote and one containing <b>test</b>. | Name displays correctly as plain text, the confirm prompt shows it, Remove works. No error, nothing strange on screen.
F2 | F | Deleting a branch re-gates its staff | High | A throwaway test branch with an exclusion covering Employee A; agent released. | Organisation -> Branches -> Delete that branch. Watch the agent. | Within ~15s the agent returns to the wall. Row disappears from Gate Exclusions.
F3 | F | A retired PC stops locking out its former user | Medium | Employee A Excluded; test PC Machine-level Required; agent walled. | Devices -> unbind the test PC. Watch the agent / sign in again. | The Required no longer applies; Employee A's own exclusion takes effect and they can work.
F4 | F | Super Admin can open the screen | Medium | - | Sign in as Super Admin. Open Gate Exclusions. | Screen loads with no error message in the table area.
F5 | F | Ordinary employees cannot see or change any of this | Critical | - | Sign in to the console with a plain Employee self-service login. | No Gate Exclusions menu, no Biometric menu, no way to change a gate setting. Only their own read-only tabs.
F6 | F | Monitoring still works for an excluded employee | High | Employee A excluded and working. | Leave the agent running 10 minutes with normal activity. Check Live Dashboard, Screenshots, Usage & Compliance. | Employee A active, screenshots arriving (if policy enables them), app/web usage recorded - as for anyone else.
Group G - Nothing else broke
G1 | G | A normal punch still opens the gate | Critical | All exclusions removed; Employee A walled. | Import an IN punch for TEST-A dated now. Watch the agent. | Released within ~15s plus sync time. Punch log shows it; Attendance shows the check-in.
G2 | G | A punch that arrives late is still recorded | High | Employee A excluded and already working. | Import an IN punch for TEST-A timestamped earlier this morning. Check Attendance for today. | Punch appears in the log and in today's attendance record. Being excluded did not stop it being recorded.
G3 | G | The mid-day out-punch behaviour is unchanged | Medium | No exclusion; Employee A punched in and working. | Import an OUT punch dated now; wait; import an IN punch a few minutes later. | Same as before this release - an out-of-office break opens on the OUT and closes on the return IN.
G4 | G | The emergency override still works | High | No exclusions; Employee A walled. | An admin issues the emergency gate override for Employee A, with a reason. Watch the agent. | Released within ~15s; the override is recorded against the approving admin.

## Summary
Run summary
These count themselves from the Test Results tab. Fill in the run details and the recommendation.
Total test cases | 37
Passed | 0
Failed | 0
Blocked | 0
Not yet run | 37
Critical cases failed | 0
Run details
Tested by | e.g. Ravi Sharma
Date started
Date finished
Console build / version
Agent version
Environment (URL)
Recommendation
Choose one:
Anything else we should know
If A2 fails, stop the whole run and tell the team straight away - that is the case the entire fix exists for.

## How to fake a punch
Simulating a door punch - no reader needed
Step 1 - map each test employee (once only)
Biometric screen -> 'Map biometric ID -> employee'. Enter a made-up device ID and pick the employee.
Use TEST-A for Employee A and TEST-B for Employee B. Save each one.
Step 2 - import a punch whenever a case needs one
Create punch.csv in Notepad with exactly these two lines (change the date and time to now):
biometric_employee_id,punch_type,punched_at
TEST-A,IN,2026-08-19 09:05:00
Biometric screen -> 'Import punches (CSV)' -> choose the file -> Import.
You should see: Imported 1 punches. The punch appears in the Punch log and the employee's gate opens.
Notes
Use OUT in the punch_type column to punch out.
To test 'no punch today', simply do not import one - and if you already have, use a date in the past.
The header row is required. Keep the file handy; you will use it repeatedly.
Reading the agent
Gate CLOSED: full-screen panel headed 'Punch in at the door to start', pulsing 'Waiting for your gate punch...'.
Gate OPEN: that panel disappears and the normal dashboard appears.
The agent re-checks every 15 seconds - after any console change, watch it for at least 20 seconds before calling a failure.